## sched_tracking (hidden)
Slab Rehabilitation Works - Olaya Towers (Tracking)
Title: Schedule of Remaining Works
Consultant: Khatib & Alami (K & A)
Contractor: Nesma & Partners
Specialist: CCL Gulf Prestressed Concrete LLC
Project: Olaya Towers
Date: 2023 - 12 - 11
Description | Nov - 2023 |  |  |  | Dec - 2023 |  |  |  | Jan - 2024 |  |  |  | Feb - 2024
| Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4 | Week-1 | Week-2 | Week-3 | Week-4
| 2023-11-11 | 2023-11-18 | 2023-11-25 | 2023-12-02 | 2023-12-09 | 2023-12-16 | 2023-12-23 | 2023-12-30 | 2024-01-06 | 2024-01-13 | 2024-01-20 | 2024-01-27 | 2024-02-03 | 2024-02-10 | 2024-02-17 | 2024-02-24
Main Part (Grooves & Filling)
B2 - Part 3
B2 - Part 4 | bar: 2023-11-11
B2 - Part 5 | bar: 2023-11-18 to 2023-11-25
B3 - Part 1 | bar: 2023-12-02
B3 - Part 2 | bar: 2023-12-09
B3 - Part 3 | bar: 2023-12-16
B3 - Part 4 | bar: 2023-12-23
B3 - Part 5 | bar: 2023-12-30
CFRP Installation | bar: 2024-01-06
B1 - Part 3 | bar: 2024-01-13
B1 - Part 4 | bar: 2023-11-11; 2024-01-20
B1 - Part 5 | bar: 2023-11-18 to 2023-11-25; 2024-01-27
B2 - Part 1 | bar: 2023-12-02
B2 - Part 2 | bar: 2023-12-09
B2 - Part 3 | bar: 2023-12-16
B2 - Part 4 | bar: 2023-12-23
B2 - Part 5 | bar: 2023-12-30
B3 - Part 1 | bar: 2024-01-06
B3 - Part 2 | bar: 2024-01-13
B3 - Part 3 | bar: 2024-01-20
B3 - Part 4 | bar: 2024-01-27
B3 - Part 5 | bar: 2024-02-03

## Summary
Date: | 2024 - 03 - 24
Summary
Sr. # | Description | Cost (PKR)
1 | Bricks + Cement + Steel | 7925000
2 | Other Materials | 2554500
3 | Labor | 3865000
| Total COST: | 14344500

## Main BOQ
Date : | 2024 - 03 - 24
Project : | Personal House Costing Plan
BOQ for Materials and Labor - Type 1 [Rev-00]
Sr. # | Description | Type | Unit | Qty | Unit Price (PKR) | Total Cost (PKR) | Remarks
1 | Design (Drawings + Structural) |  | LS | 1 | 500000 | 500000
2 | Excavation of foundations | 3 ft | LS | 1 | 75000 | 75000 | Reference from a 5 marla plot online costing ref.
3 | Termite Spray | 8 bottles | LS | 1 | 60000 | 60000
4 | Broken Brick (Rorri) |  | ft3 | 2400 | 90 | 216000
5 | Aggregate (Bajri) |  | ft3 | 3600 | 135 | 486000
6 | Sand - Filling |  | ft3 | 7500 | 40 | 300000
7 | Sand - Plaster |  | ft3 | 3000 | 65 | 195000
8 | Bricks - 1st class |  | Pcs | 150000 | 18 | 2700000
9 | Cement (Grade-A) | Maple Leaf | Pcs | 1800 | 1250 | 2250000
10 | Filling | 5 ft depth | LS | 1 | 250000 | 250000
11 | DPC |  | LS | 1 | 25000 | 25000
12 | Lintels | 16 gauge | Pcs | 35 | 8500 | 297500
13 | Steel - Grade 60 |  | Kgs | 8500 | 350 | 2975000 | Assumed for Grade-80 from 60
14 | Gate |  | LS | 1 | 250000 | 250000
15 | Piping | PPR | LS | 1 | 125000 | 125000
16 | Sewerage system |  | LS | 1 | 350000 | 350000
17 | Labor Rate |  | Sqm | 7200 | 450 | 3240000 | 14 marlas x 2 (double storey)
18 | Site Watcher |  | Pcs | 3 | 25000 | 75000
19 | Food for labor |  | LS | 1 | 50000 | 50000
[5 empty] | Total Cost | 14419500

## Phase-11 (hidden)
STRAND SCHEDULE
Sr. # | GROUP | LENGTH (MM) | NO'S
1 | Group-1a | 71000 | 9
2 | Group-2 | 3800 | 3
3 | Group-3 | 3800 | 3
4 | Group-4 | 3800 | 3
5 | Group-5 | 3800 | 3
6 | Group-6 | 3800 | 3
7 | Group-7 | 4000 | 3
8 | Group-8 | 4650 | 3
9 | Group-9 | 3800 | 3
10 | Group-10 | 3800 | 3
11 | Group-21 | 3800 | 3
12 | Group-22 | 3800 | 3
13 | Group-22b | 4300 | 1
14 | Group-23 | 3800 | 3
15 | Group-24 | 3800 | 3
16 | Group-25 | 3800 | 3
17 | Group-26 | 4100 | 3
18 | Group-27 | 4600 | 10
19 | Group-27b | 4970 | 4
20 | Group-28a | 71000 | 15
21 | Group-29 | 3800 | 3
22 | Group-40 | 14600 | 11
23 | Group-40b | 13100 | 3
24 | Group-40c | 1500 | 8
25 | Group-40d | 7700 | 2
26 | Group-41 | 11660 | 7
27 | Group-41b | 6650 | 3
28 | Group-42 | 32920 | 9
29 | Group-43 | 5000 | 11
30 | Group-43b | 3370 | 3
31 | Group-44 | 16100 | 7
32 | Group-44b | 6760 | 4
33 | Group-45 | 4500 | 5
34 | Group-46 | 15880 | 12
35 | Group-54 | 12760 | 3
36 | Group-55 | 4100 | 3
37 | Group-56 | 58700 | 1
38 | Group-57 | 11850 | 1
39 | Group-58 | 1500 | 14

## Phase-11b (hidden)
STRAND SCHEDULE (Ph-11b)
Sr. # | GROUP | LENGTH (MM) | NO'S
1 | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF!

## Phase-13 (hidden)
STRAND SCHEDULE (Ph-13)
Sr. # | GROUP | LENGTH (MM) | NO'S
1 | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF!
26 | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF!

## Phase-14 (hidden)
STRAND SCHEDULE (Ph-14)
Sr. # | GROUP | LENGTH (MM) | NO'S
1 | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF!